## Basic Risk Assessment
Delivery Agent System
RISK TYPE | RISK DESCRIPTION | AFFECTS (project,product,bussiness) | PROBABILITY LEVEL | IMPACT LEVEL | PREVENTION MEASURES | Name
Security Vulnerabilities | System safety risks, vulnerabilities in the system, data leaks, data injection attacks or cyberattacks. | Business | Medium | High | Regularly conduct penetration tests, Implement strong encryption, input validation and parametrized queries to access database. | Constantinos P. | LEVEL KEY
Data Privacy Concerns | Risks related to improper management or granting unauthorised access to customer's private information. | Business | Medium | High | Implement data privacy protocols. Regular authorization and authentication checks for the users. | Constantinos P. | High
Changes to the Requirements | Requirement or scope changes that directly affect the system, alterating critical details of the application application resulting in project creep. | Project, Product | Medium | High | During the first project planning phase, requirements must carefully explained and obtained. Establish frequent inspection meetings to compare and verify that the project's present condition follows the obtained requirements. | Constantinos P. | Medium
Time Constraints | Innacurate time estimates or tight schedule of tasks can cause the working team to produce poor product or no product at all. | Product | Medium | Medium | The project manager should create a plan before hand with clear instruction to the teams analyzing all key requirments that the project needs to be developed. Ensure proper time allocation for each task and proactively allow for extra time in case something unexpected happens during the project development. | Constantinos P. | Low
Medical Related Staff Issues | Key personnel must take a sick leave, therefore unavailable to work. Tasks are postponed and milestones are delayed. | Project | Medium | Medium | Employees should receive training in order to be able to fill in for one another. Select support personnel who can fill in if any key members of the team is absent, and make sure project-related information is well-documented. Enable working from home to prevent sick employees coming into contact with the others. | Constantinos P.
Product Competition | Application might be developed from other company, advertized or released earlier. | Business | High | Medium | Team should focus on keeping the time schedule as is and deliver in timeframes established. The marketing team should strategize how to compete and collect information from the competition to avoid mistakes they made and deliver a better overall product. | Alexios
Management Changes | The Project Manger or important stakeholders change during development. | Project | Low | High | Make sure that the manager is commited to the project. Make sure the project contract ensures that such changes are not easy to occur without serious reasons. Have replacement personnel to take over if needed. | Alexios
Scalability Constraints | Inability to handle a sudden increase in delivery requests, causing system slowdowns or outages. | Product | Low | High | Design the system to be able to scale according to the needs of the business, employ cloud-based services, and conduct load testing regularly. | Alexios
Miscommunication | Miscommunication or misunderstanding of tasks between the team members. | Product | Medium | Medium | Create distinct communication channels and protocols. Maintain regular status meetings and daily briefing sessions. | Stefanos
Budget | Budget Overruns. | Product | Medium | High | Create a detailed budget plan and keep close tabs on project expenses. Managing tasks according to schedule allows budget to stay consistent with the project planning and estimations. | Stefanos
Stakeholders Involvevment | Lack of stakeholder involvement. | Project | Low | Medium | Effectively communicate with stakeholders. Include them in important decision-making processes. Conduct interviews that not only gain useful insights from stakeholders but also informs them about their stakes on the project. | Stefanos
Third-Party Dependencies | Software is heavily dependent on third-party services. Can lead to inconsistencies and delays. | Product | High | High | Prepare a backup plan. Choose third-party services that are dependable and well-maintained, make sure that the company doesn’t have alternatives that will reduce the third-party dependencies before making any purchases, contracts. | Stefanos
Integration | Integrating the product to existing products or parts of a product. | Product | Medium | High | Create a detailed integration strategy. Perform regular integration testing to identify and resolve issues. | Stefanos
Compatibility | The software not being compatible between different browsers, devices or operating systems. | Product | Medium | High | Ensure that the final product will allow all kinds of users to use with the same ease and performance as others. Develop cross platform software, and focus on a web responsive design. | Constantinos K.
Law Changes | Law changes may force unexpected changes to the project in order to oblidge to the new laws and avoid lawsuits. | Project | Low | Medium | The Project manager must keep an eye on the news and be aware of trends that may cause law changes. Usually such changes in the legal system take time, so the project manager must use this time effectively to incorporate the new changes without severly affecting the final product. | Constantinos K.
Lack of Customers | Problems convincing customers to prefer our product over our competitors. | Business | Medium | High | The Marketing team must create smart strategies to attract customers, by showcasing the benefits of our profuct and create offers for new customers. | Constantinos K.
Enviromental Changes | Pandemics or other enviromental related issues may affect the success of our product. | Business | Low | High | The delivery agent system must include features that will prevent enviromental changes to affect the usage of our product. E.g.(Drone Delivery) | Constantinos K.